## Distribution of Social Housing
Municipal District | Settlement | No. of Households on SSHA (1st Choice) | No. of Households on Transfer List (HAP/RAS/Leasing tenants only 1st choice) | % of Demand by Settlement | 2022 – 2026 Target Distributed by Demand | Approved Delivery | Outstanding Delivery per MD | Proposed Delivery by MD/Division/Settlement
Castlebar | Balla | 14 | 23 | 1.47 | 2 | 0 | 2 | 2
| Ballyvary | 3 | 2 | 0.2 | 11 | 11 | 0 | 11
| Carnacon | 1 | 0 | 0.04 | 9 | 9 | 0 | 9
| Castlebar | 324 | 456 | 30.95 | 283 | 22 | 261 | 283
| Glenisland | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Killawalla | 3 | 2 | 0.2 | 0 | 0 | 0 | 0
| Lahardane | 0 | 2 | 0.08 | 8 | 0 | 8 | 8
| Mayo Abbey | 3 | 1 | 0.16 | 0 | 0 | 0 | 0
| Parke | 2 | 0 | 0.08 | 0 | 0 | 0 | 0
| Tourmakeady | 2 | 1 | 0.12 | 5 | 0 | 5 | 5
Ballina | Attymass | 1 | 0 | 0.04 | 0 | 0 | 0 | 0
| Ballina | 132 | 345 | 18.93 | 179 | 56 | 123 | 179
| Ballycastle | 3 | 7 | 0.4 | 3 | 0 | 3 | 3
| Bonniconlon | 4 | 9 | 0.52 | 0 | 0 | 0 | 0
| Crossmolina | 9 | 16 | 0.99 | 17 | 0 | 17 | 17
| Kilifan | 0 | 1 | 0.04 | 0 | 0 | 0 | 0
| Killala | 2 | 13 | 0.6 | 10 | 0 | 10 | 10
| Moygownagh | 2 | 0 | 0.08 | 0 | 0 | 0 | 0
| Knockmore | 1 | 3 | 0.16 | 0 | 0 | 0 | 0
| Keenagh | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Carrowmore / Lacken | 0 | 0 | 0 | 0 | 0 | 0 | 0
Claremorris/Swinford | Ballindine | 8 | 12 | 0.79 | 4 | 0 | 4 | 4
| Ballinrobe | 28 | 32 | 2.38 | 43 | 0 | 43 | 43
| Ballyhaunis | 43 | 58 | 4.01 | 25 | 0 | 25 | 25
| Bohola | 7 | 4 | 0.44 | 0 | 0 | 0 | 0
| Charlestown | 24 | 29 | 2.1 | 15 | 0 | 15 | 15
| Claremorris | 62 | 95 | 6.23 | 64 | 26 | 38 | 64
| Cross | 0 | 0 | 0 | 8 | 8 | 0 | 8
| Foxford | 26 | 35 | 2.42 | 5 | 0 | 5 | 5
| Hollymount | 2 | 1 | 0.12 | 2 | 2 | 0 | 2
| Irishtown | 3 | 1 | 0.16 | 2 | 0 | 2 | 2
| Kilkelly | 6 | 11 | 0.67 | 2 | 0 | 2 | 2
| Kilmaine | 1 | 3 | 0.16 | 6 | 0 | 6 | 6
| Kilmovee | 2 | 1 | 0.12 | 8 | 0 | 8 | 8
| Kiltimagh | 26 | 27 | 2.1 | 24 | 21 | 3 | 24
| Knock | 18 | 20 | 1.51 | 30 | 0 | 30 | 30
| Kilasser | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Midfield | 1 | 1 | 0.08 | 0 | 0 | 0 | 0
| Swinford | 43 | 40 | 3.29 | 24 | 2 | 22 | 24
Westport/Belmullet | Achill | 14 | 13 | 1.07 | 20 | 20 | 0 | 20
| Aghagower | 3 | 0 | 0.12 | 0 | 0 | 0 | 0
| Ballycroy | 6 | 2 | 0.32 | 5 | 0 | 5 | 5
| Bangor Erris | 4 | 6 | 0.4 | 5 | 0 | 5 | 5
| Belmullet | 32 | 41 | 2.9 | 28 | 4 | 24 | 28
| Binghamstown | 0 | 4 | 0.16 | 0 | 0 | 0 | 0
| Bunnacurry | 1 | 0 | 0.04 | 0 | 0 | 0 | 0
| Carrowteige | 0 | 1 | 0.04 | 0 | 0 | 0 | 0
| Clare Island | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Corlough | 1 | 0 | 0.04 | 0 | 0 | 0 | 0
| Currane | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cuslough | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Doohoma | 2 | 0 | 0.08 | 0 | 0 | 0 | 0
| Drummin | 1 | 2 | 0.12 | 0 | 0 | 0 | 0
| Geesala | 1 | 3 | 0.16 | 0 | 0 | 0 | 0
| Glenamoy | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Glenhest | 0 | 1 | 0.04 | 0 | 0 | 0 | 0
| Inver | 1 | 2 | 0.12 | 0 | 0 | 0 | 0
| Inisturk | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kilmeena | 2 | 5 | 0.28 | 0 | 0 | 0 | 0
| Louisburgh | 8 | 15 | 0.91 | 12 | 0 | 12 | 12
| Mulranney | 8 | 5 | 0.52 | 16 | 16 | 0 | 16
| Newport | 7 | 10 | 0.67 | 27 | 0 | 27 | 27
| Pullathomas | 3 | 1 | 0.16 | 1 | 0 | 1 | 1
| Rossport | 0 | 0 | 0 | 1 | 0 | 1 | 1
| Tonragee | 0 | 1 | 0.04 | 0 | 0 | 0 | 0
| Westport | 144 | 113 | 10.2 | 100 | 67 | 33 | 100
Total |  | 1044 | 1476 | 100.03 | 1004 | 264 | 740 | 1004

## Future Programme Master Summary
Settlement | Est Part V | Existing LA Landbank where units will be built | Future Land Purchases | LA Turnkey | LA Buy and Renew | AHB CALF | AHB CAS | Social Homes via Mixed Tenure | Total Social Homes to be delivered | Comments
Balla | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Ballyvary | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11
Carnacon | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9
Castlebar | 30 | 36 | 115 | 26 | 5 | 63 | 8 | 0 | 283
Glenisland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Killawalla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lahardane | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8
Mayo Abbey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Parke | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tourmakeady | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5
Attymass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ballina | 20 | 59 | 40 | 41 | 10 | 0 | 9 | 0 | 179
Ballycastle | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
Bonniconlon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crossmolina | 2 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 17
Kilifan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Killala | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10
Moygownagh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Knockmore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Keenagh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carrowmore / Lacken | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ballindine | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4
Ballinrobe | 3 | 0 | 20 | 0 | 5 | 15 | 0 | 0 | 43
Ballyhaunis | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 0 | 25
Bohola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Charlestown | 0 | 0 | 10 | 0 | 5 | 0 | 0 | 0 | 15
Claremorris | 0 | 6 | 0 | 20 | 8 | 30 | 0 | 0 | 64
Cross | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Foxford | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5
Hollymount | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Irishtown | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Kilkelly | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Kilmaine | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6
Kilmovee | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8
Kiltimagh | 0 | 21 | 0 | 0 | 3 | 0 | 0 | 0 | 24
Knock | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 30
Kilasser | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midfield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Swinford | 0 | 0 | 15 | 0 | 5 | 0 | 4 | 0 | 24
Achill | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Aghagower | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ballycroy | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5
Bangor Erris | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5
Belmullet | 0 | 4 | 0 | 20 | 4 | 0 | 0 | 0 | 28
Binghamstown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bunnacurry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carrowteige | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Clare Island | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corlough | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Currane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cuslough | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Doohoma | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drummin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Geesala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Glenamoy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Glenhest | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inver | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inisturk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kilmeena | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Louisburgh | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 12
Mulranney | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16
Newport | 0 | 0 | 0 | 0 | 3 | 0 | 24 | 0 | 27
Pullathomas | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Rossport | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Tonragee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Westport | 10 | 50 | 20 | 0 | 3 | 17 | 0 | 0 | 100
Total | 67 | 240 | 304 | 107 | 78 | 125 | 83 | 0 | 1004

## Future Programme by Year
Year | Est Part V | Existing LA Landbank where units will be built | Future Land Purchases | LA Turnkey | LA Buy and Renew | AHB CALF | AHB CAS | Total Social Homes to be delivered | Disability | Older Persons
2022 | 2 | 21 |  | 20 | 2 | 20 | 24 | 89 | 4 | 8
2023 | 5 | 132 | 4 |  | 5 | 28 | 51 | 225 | 11 | 22
2024 | 12 | 87 | 100 | 26 | 20 | 41 | 8 | 294 | 15 | 30
2025 | 20 |  | 100 | 30 | 25 | 18 |  | 193 | 9 | 18
2026 | 28 | 0 | 100 | 31 | 26 | 18 |  | 203 | 10 | 20
Total | 67 | 240 | 304 | 107 | 78 | 125 | 83 | 1004 | 49 | 98